## GanttChart
[Moneytor] Implementation Schedule
Code convention: https://github.com/codepath/android_guides/wiki/Organizing-your-Source-Files | [13 empty] | Xem note ở bên tab "Phân công code"
| Start Implement | 2021-12-10 |  |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| SE Lead | Thành | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24
 | time axis 2021-12-06 to 2022-01-30
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-12-06 to 2022-01-30
1 | UI (view)
2021-01-01 | Main screen | Hiếu |  |  | - |  | 100% | 0
2021-01-01 | Spending List | Hiếu |  | 2021-12-10 | 2021-12-14 | 5 | 100% | 3
2021-01-01 | Spending Note (detail) | Uyên |  | 2021-12-12 | 2021-12-16 | 5 | 100% | 4
2021-01-01 | Goal List | Hiếu |  | 2021-12-10 | 2021-12-14 | 5 | 100% | 3
2021-01-01 | Goal Note (detail) | Uyên |  | 2021-12-12 | 2021-12-16 | 5 | 100% | 4
2021-01-01 | Debt List | Hiếu |  |  | - |  | 100% | 0
2021-01-01 | Note Debt (detail) | Uyên |  |  | - |  | 100% | 0
2021-01-01 | Contact list | Hiếu |  | 2021-12-15 | 2021-12-16 | 2 | 100% | 2
2021-01-01 | Category list | Hiếu |  | 2021-12-16 | 2021-12-17 | 2 | 100% | 2
2021-01-01 | Time period list | Hiếu |  |  | - | 2 | 100% | 0
2021-01-01 | Analyze | Uyên |  |  | - |  | 100% | 0
2021-01-01 | Visualize (Pie chart) | Uyên |  |  | - |  | 100% | 0
2021-01-01 | Visualize (Bar chart) | Uyên |  |  | - |  | 100% | 0
2021-01-01 | Setting | Bình |  |  | - |  | 100% | 0
2021-01-01 | Dialog box | Hiếu |  |  | - |  | 100% | 0
2021-01-01 | Custom notification | Bình |  |  | - |  | 100% | 0
2021-01-01 | Login | Bình |  | 2021-12-17 | 2021-12-19 | 3 | 100% | 1
2 | Database (model)
.1 | SpendingNote (model & DAO) | Thành |  | 2021-12-11 | 2021-12-11 | 1 | 100% | 0
.1 | DebtLend (model & DAO) | Hoàng |  | 2021-12-11 | 2021-12-11 | 1 | 100% | 0
.1 | SpendingGoal (model & DAO) | Hoàng |  | 2021-12-11 | 2021-12-11 | 1 | 100% | 0
.1 | Wallet (model & DAO) | Thành |  | 2021-12-11 | 2021-12-11 | 1 | 100% | 0
.1 | Relate (model & DAO) | Thành |  | 2021-12-12 | 2021-12-12 | 1 | 100% | 0
.1 | Reminder (model & DAO) | Hoàng |  | 2021-12-12 | 2021-12-12 | 1 | 100% | 0
.1 | RoomDatabase | Hoàng |  | 2021-12-13 | 2021-12-14 | 2 | 100% | 2
.1 | Repository (DAO model cho hết vào đây) | Hoàng, Thành |  | 2021-12-13 | 2021-12-14 | 2 | 100% | 2
.1 | Firebase | Bình |  | 2021-12-17 | 2021-12-22 | 6 | 100% | 4
3 | Service (viewmodel, logic)
.1 | SpendingViewModel | Thành |  | 2021-12-14 | 2021-12-14 | 1 | 100% | 1
.1 | DebtLendViewModel | Hoàng |  | 2021-12-14 | 2021-12-14 | 1 | 100% | 1
.1 | SpendingGoalViewModel | Hoàng |  | 2021-12-15 | 2021-12-15 | 1 | 100% | 1
.1 | Spending Detail ViewModel | Thành |  | 2021-12-15 | 2021-12-15 | 1 | 100% | 1
.1 | Goal Detail ViewModel | Thành |  | 2021-12-15 | 2021-12-15 | 1 | 100% | 1
.1 | DebtLend Detail ViewModel(xử lý request thêm sửa xóa 1 note) | Hoàng |  | 2021-12-16 | 2021-12-16 | 1 | 100% | 1
.1 | Filter Category | Thành |  |  | - |  | 100% | 0
.1 | Filter Time | Thành |  |  | - |  | 100% | 0
.1 | Analyze | Hoàng |  |  | - |  | 100% | 0
.1 | Visualize | Hoàng |  |  | - |  | 100% | 0
.1 | Contact list (recyclerview) | Bình |  | 2021-12-14 | 2021-12-16 | 3 | 100% | 3
.1 | Setting | Bình |  | 2021-12-23 | 2021-12-24 | 2 | 100% | 2
.1 | Push notification (API) | Bình |  | 2021-12-10 | 2021-12-13 | 4 | 100% | 2
.1 | Login google | Bình |  | 2021-12-19 | 2021-12-20 | 2 | 100% | 1
TEMPLATE ROWS
See the Help worksheet to learn how to use these template rows. You can hide these rows before printing.
1 | [ Level 1 Task, Category, or Phase ]
.1 | . [ Level 2 Task ] |  |  |  | - |  | 0% | 0
.1 | . . [ Level 3 Task ] |  |  |  | - |  | 0% | 0
.1 | . . . [ Level 4 Task ] |  |  |  | - |  | 0% | 0
► Watch How to Create a Gantt Chart in Excel

## Phân công code
UI |  | Database |  | Service (Business logic)
Login | Bình | Firebase | Bình | Push Notification (Daily, ngày cụ thể) | Bình
Main screen |  | Room | Hoàng | Login google | Bình
Spending List | Hiếu | Repository | Thành, | CRUD a Spending | Thành
Goal List | Hiếu | SpendingNote | Thành | CRUD a Goal | Thành
Debt List |  | DebtLend | Hoàng | CRUD a Debt/Lend | Hoàng
Analyze |  | SpendingGoal | Hoàng | Setting (set daily reminder, on/off widget) | Bình
Setting |  | Wallet | Thành | Visualize | Hoàng
HomeScreen widget |  | Relate | Thành | Analyze | Hoàng
Note Spending (detail) | Uyên | Reminder | Hoàng | Filter Category | Thành
Note Debt (detail) |  |  |  | Filter Time | Thành
Goal Note (detail) | Uyên |  |  | List Spending (viewmodel tương tác database) | Thành
Set reminder |  |  |  | List Debt (viewmodel tương tác database) | Hoàng
Custom notification | Bình |  |  | List Goal (viewmodel tương tác database) | Hoàng
Contact list |  |  |  | Contast list (intent lấy danh bạ) | Bình
Category list
Time period list
Visualize (Pie chart)
Visualize (Bar chart)
Dialog box (để confirm khi user xóa note, set reminder)
Code Convention
https://github.com/codepath/android_guides/wiki/Organizing-your-Source-Files
|  |  | Architecture | Component
|  | Note: | MVVM | View: UI, XML, Activity/Fragment | Tất cả về giao diện (chỉ xử lý logic đơn giản , còn cái nào dài quá (liên quan tới model) thì ném viewmodel qua lời gọi hàm) (Cần lưu object ViewModel, muốn làm gì thì delegate cho viewModel làm)
|  |  |  | ViewModel: business logic | Xử lý tất cả logic Nhận event từ UI và làm theo yêu cầu tương tác với model (sử dụng LiveData/MutableLiveData để binding tự động giữa UI và model)
|  |  |  | Model: POJO, database | Model chỉ cần getter/setter đơn thuần là để store data

## GanttChartPro
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The versions designed for Excel 2010+ use the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Learn More About Gantt Chart Template Pro

## TermsOfUse
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2018 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html