## Test Summary Report
Project: MoneyTor
Team: Group 14
ID | Feature Name | Description | Tester | Remark
UC01 | Add spending note | User can add, update, delete a spending note | LTHieu
UC02 | Add debt/lend note | User can add, update, delete a debt or lend note | NDTTHanh
UC03 | Add spending goal | User can add a goal in the future and receive notification when the goal is about to due | LCBinh
UC04 | Add contact | Select contacts who share a spending with user, or who is the user's target in debt/lend | NMUyen
UC05 | Search or filter spendings | Search for a spending's title or description, or filter to show spendings with given conditions | DNDHoang
| Số lượng function được test | 5
| Số lượng Test Cases | 29
| Số lượng Test Cases Pass | 22
| Số lượng Test Cases Failed | 7
| ID | Tổng số Test Case | Số lượng Test Case Pass | Số lượng Test Case Failed
| UC01 | 6 | 6 | 0
| UC02 | 7 | 3 | 4
| UC03 | 5 | 4 | 1
| UC04 | 6 | 4 | 2
| UC05 | 5 | 5 | 0

## Test Reports
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B01 | Unable to select new contact in debt/lend when another already exists without deselecting the old one | In Manage debt/lend screen: 1. Tap on "Target" field 2. Tap on items to select: "Hieu", "Hieu1" 3. Press on Save button Expected: "Hieu" is checked, then "Hieu" is unchecked and "Hieu1" is checked Actual: Only "Hieu" is checked (must tap on "Hieu" again to unchecked) | UC04 | Low | NMUyen | 2022-01-24 | Open
B02 | Unable to add contacts when some have already existed without removing them | At "Share with" field in Add spending screen, "Hieu", "Hieu1" were chosen 1. Tap on "Share with" field 2. Tap on contact items "Hieu2", "Hieu3" to select 3. Press on Save button Expected: The chosen list includes "Hieu", "Hieu1", "Hieu2", "Hieu3" Actual: The chosen list includes "Hieu2", "Hieu3" | UC04 | Medium | NMUyen | 2022-01-24 | Open
B03 | No notice displayed when user doesn't input Target | 1. Press Add Floating action button 2. Press on ""Save"" button" Expected: a notice displayed on Target text field Actual: no notice displayed | UC02 | Low | NDTThanh | 2022-01-24 | Close
B04 | No notice displayed when amount input too large | 1. Press Add Floating action button 2. Enter Amount: 9999999999999999999999999 3. Press on Target text field 4. Select 1st target in contact list 5. Press on ""Save"" button" Expected: A limited amount notice will be displayed on Amount textfield when input over 10^12 Actual: No notice dispalyed | UC02 | Low | NDTThanh | 2022-01-24 | Open
B05 | Can't delete a debt/lend note | 1. Press on second note in debt/lend list 2. Press on "Delete" button Expected: delete successfully Actual: Note isn't removed from list | UC02 | High | NDTThanh | 2022-01-24 | Close
B06 | Can't delete any debt/lend note | 1. Press on first note in debt/lend list 2. Press on "Delete" button 3. Repeat step 1-2 until no note left Expected: no note left Actual: can't delete any note | UC02 | High | NDTThanh | 2022-01-24 | Close
B07 | Invalid day not prevented | 1. Press on the Add floating action button 2. Enter date in the past, for example: 31/12/2020 Expected: A warning show up, the date field is cleared Actual: The goal was added, despite the deadline set in the past | UC03 | High | LCBinh | 2022-12-24 | Open